## Sheet1
| Phase | Address | BR | Sq. Ft. | Building Type | Unit Type | All Rooms |  | Kitchen | Kitchen |  |  | APPLIANCE REMOVAL |  |  |  |  | Bathrooms |  |  |  |  | Door
[7 empty] | Paint | Flooring | Countertop | Cabinet Doors | Cabinet Box | Other | Refrigerator | Stove | Dishwasher | Washer | Dryer | Resurface Tub | Vanity top | Vanity Base | Toilets | Comments | Bedroom | Common | Bathroom | Other | Patch Walls | Ceiling Texture | Minor Repairs | Number of Smoke Detectors to Replace | Window Blinds | Cleaning | Trash- Out | Other
0334 | 2 | 624 Bryant Avenue North, Apt 102 | 2 | 1196 | G5 | Garden | Yes | Install vinyl in entire unit. | Resurface | Strip and paint cabinet, 1 drawer front missing. | N/A | Repair under the sink and new vent hood | N/A | Remove | N/A | N/A |  | Resurface 1 Tub Bath 1 | Replace vanity top Bathroom 2. | Replace vanity Bathroom 2 | Replace Bathroom 2 toilet | N/A | Bedroom 2 needs new lock set on entry door. | N/A |  | N/A | N/A | N/A | Replace the intake air vent, and replace the light fixture in the utility room. Replace switch plate covers. | 4 | No | Yes | N/A | N/A
0334 | 2 | 725 Lyndale Avenue North, Apt. 202 | 2 | 971 | G1A | Garden | Yes | Replace with vinyl in entire unit | Resurface | Strip and paint cabinet | N/A | N/A | N/A | N/A | Remove | N/A | N/A | Resurface 1 Tub Bath 1 | N/A | Vanity doors need adjusting in both bathrooms | N/A | Need Toilet Paper Holder | Bedroom 2 closet door needs adjusting, entry door needs new keeper. | N/A |  | Hallway Closet door needs adjusting | Small hole in Bedroom 1, small hole in the hallway | N/A | Need new vents. Remove call button in Bedroom 1. Replace switch plate covers. | 4 | Yes | Yes | N/A | N/A
0334 | 2 | 725 Lyndale Avenue North, Apt. 301 | 2 | 865 | G1A | Garden | Yes | Replace with vinyl in entire unit | Resurface | Strip and paint cabinet. | N/A | Replace Faucet | N/A | N/A | N/A | N/A | N/A | Resurface 1 Tub Bath 1 | Replace top in Bath 1 | Replace vanity Bath 1 | N/A | Replace faucet in Bath 1 | Replace entry door lockset in Bedroom 1. Adjust closet door in Bedroom 2 | N/A |  | N/A | N/A | N/A | Replace intake air vent. Replace switch plate covers. | 4 | Yes | Yes. Shampoo Carpet. | Minor trash | N/A
0334 | 2 | 725 Aldrich Avenue North, Apt. 301 | 2 | 865 | G1A | Garden | Yes | Replace vinyl in kitchen, bath and living. Clean carpet in bedrooms | Resurface | Strip and paint cabinets. Missing some hardware and need adjusting. | N/A | Replace vent hood, replace light fixture. | N/A | Remove | N/A | N/A | Remove | Resurface 1 Tub Bath 1 | Replace top in Bath 1 | Replace vanity Bath 1 | Replace toilet seat | Replace Toilet paper holder | Fix door stop in Bedroom 2 | N/A | Replace entry door 36"LH | N/A | Minor patching in kitchen, existing repairs need sanding and additional mud. | N/A | Replace intake air vent. Replace switch plate covers. | 4 | Yes | Yes | N/A | N/A
0334 | 2 | 718 Aldrich Avenue North, Apt. 102 | 3 | 1176 | G1D | Garden | Yes | Replace carpet with vinyl in living, hallways and bedrooms | Resurface | Strip and paint, hardware needs adjusting | N/A | Replace vent hood, replace faucet. | N/A | Remove | N/A | N/A | N/A | Resurface tubs in both bathrooms | Replace in both bathrooms | Replace in both bathrooms | Replace toilet seat Bathroom 2 | Replace faucets in both bathrooms | Lockset on entry doors in Bedrooms 1, 2 and 3. Patch small hole in entry door in Bedroom 3. | Replace lockset on hallway closet | N/A | N/A | Corners in the Kitchen need repair. Small mirror glued to the wall in the hallway. | Length of tub 4" wide, corner of wall and ceiling in both bathrooms. 30" x12" area above the tub in Bathroom 2 | Replace intake air vent. Replace switch plate covers. | 5 | Yes | Yes | N/A | N/A
0073 | 4 | 700 5th Avenue North, Apt. 202 | 2 | 953 | G3A | Garden | Yes | Replace with vinyl in entire unit | Resurface | Adjust doors and replace missing hardware. | Paint by stove | N/A | N/A | N/A | N/A | Remove | N/A | N/A | Replace vanity top | Paint vanity base | N/A | N/A | Entry door hardware needed in both bedrooms | N/A | N/A | N/A | N/A | N/A | Remove call button in Bedroom 1. Replace switch plate covers. | 4 | Yes, except Bedroom 2. | Yes | N/A | N/A
0073 | 4 | 900 5th Ave. North, Apt. 102 | 3 | 1232 | G1D | Garden | Yes | Vinyl in laundry room. Clean carpet. | Resurface | 2 Drawers, one door needs repair. | N/A | Vent covers need replaced | Remove | N/A | N/A | N/A | N/A | N/A | Replace vanity including top in bath 2. | Missing handles on vanity in Bathroom 2. | Replace in Bathroom 2. | Bathroom 1 needs toilet paper holder. | N/A | N/A | N/A | N/A | N/A | N/A | Need door stops in Bedrooms 2 and 3. New vents in hallway. Replace switch plate covers. | 5 | Yes | Yes. Shampoo Carpet. | N/A | N/A
0073 | 4 | 1016 5th Ave. North | 3 | 1340 | 5uT-ER | Townhouse | Yes | Yes, vinyl in kitchen and clean carpet in other rooms. Need repair by front door. | Resurface | 1 drawer front missing. Cabinets are mismatched. Paint wood cabinets white. | N/A | N/A | N/A | N/A | N/A | Remove | N/A | N/A | N/A | N/A | Needs toilet seat in Bathroom 1. | Bathroom 1 needs toilet paper holder. | Door From Bedroom 1 to Bathroom needs replacing has a hole. | Utility room door missing hardware | Door to bathroom 3 will not open. | N/A | Living room 2 inch hole. | N/A | Need door stops in Bedrooms 1 and 2. Replace switch plate covers. | 5 | Yes | Yes. Shampoo Carpet. | N/A | Top section of banister need secure and ballista reinstalled.
0058 | 3 | 1000 Aldrich Avenue North Apt. 101 | 2 | 953 | G3A | Garden | Yes | Replace floor in entire unit with vinyl . | N/A | Missing 2 dummy drawer fronts | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 1 door in Bedroom 2 missing | N/A | N/A | N/A | N/A | N/A | Replace switch plate covers. | 4 | Yes | Yes | Major trash. Rooms full of furniture. | N/A
0058 | 3 | 1001 11th Avenue North Apt. 301 | 2 | 902 | G1D | Garden | Yes | Remove carpet in living room, hall, and bedrooms and replace with vinyl. | N/A | Strip and paint cabinets. Missing some hardware and need adjusting. | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Resurface tub | N/A | Replace vanity | N/A | Replace closet shelves | N/A | Replace hall closet door | Lock set missing | N/A | N/A | N/A | Replace switch plate covers. | 4 | Yes | Yes | Major trash. Some furniture. | N/A
0058 | 3 | 1021 7th Street North Apt. 202 | 2 | 1045 | G1C | Garden | Yes | Remove carpet in living room, hall, and bedrooms and replace with vinyl. | Resurface | Strip and paint cabinets. Missing some hardware and need adjusting. | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Resurface tubs in both bathrooms. | Replace tops in both bathrooms | Paint inside vanity in both bathrooms | N/A | Bathroom 1 missing towel bar and toilet paper holder | Replace 1 closet door in Bedroom 2, small hole | N/A | N/A | Reinstall all locksets, in unit, removed for painting. | N/A | N/A | Replace covers on hallway lights. Replace switch plate covers. | 4 | Yes | Yes | Minor trash removal. | N/A
332a | 1 | 1102 Olson Memorial Highway Apt 201 | 2 | 865 | G1A | Garden | Yes | New vinyl in entire unit | Resurface | Strip and paint cabinets. | N/A | N/A | Remove | Remove | Remove | N/A | Remove | N/A | Replace vanity top | Replace vanity base | Replace 1 toilet | N/A | N/A | Back door is glass is broken. | N/A | N/A | N/A | Small area in kitchen | Broken window in living room, windows sash in Bedroom 1 need deep cleaning or replacement. Electric socket in Bedroom 1 is burnt. Replace switch plate covers. | 4 | Yes | Yes | Major trash | Needs new water heater.
332a | 1 | 1102 Olson Memorial Highway Apt 203 | 1 | 743 | G1A | Garden | Yes | New vinyl in entire unit | Resurface | Strip and paint cabinets. | N/A | Replace faucet | Remove | Remove | N/A | N/A | N/A | Resurface tub | Replace vanity top | Replace vanity base | Replace 1 toilet | Needs base trim | N/A | N/A | N/A | N/A | N/A | N/A | Replace switch plate covers. | 3 | Yes | Yes | Major trash | N/A
0334 | 2 | 700 Olson Memorial Highway Apt 102 | 1 | 743 | G1C | Garden | Yes | Clean carpet | Resurface | Hardware needs adjusting | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Needs new hinges | Replace 1 toilet | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Replace switch plate covers. | 3 | Yes | Yes. Shampoo carpet | Minor trash | N/A
0334 | 2 | 718 Aldrich Avenue North Apt. 302 | 3 | 1207 | G1D | Garden | Yes | Replace carpet in living room, hall and bedrooms with vinyl. Replace vinyl in Bathroom 1. | Resurface | Strip and paint cabinets. | N/A | N/A | Remove | Needs knobs | N/A | N/A | N/A | Resurface tub in Bathroom 1. | Replace vanity top in Bathroom 1 | Adjust doors in Bathroom 1, missing one door in Bathroom 2 | Replace 1 toilet, bathroom 1 | N/A | Adjust closet doors in Bedroom 1. | N/A | N/A | N/A | Need repairs on two corners in the kitchen, previous repair needs sanding and additional mud. | N/A | Replace switch plate covers. | 5 | Yes | Yes | N/A | N/A
0334 | 2 | 718 Aldrich Avenue North Apt. 103 | 2 | 887 | G1D | Garden | Yes | Clean carpet | Resurface | Strip and paint cabinets,1 door missing. Hardware needs adjusting. | N/A | Replace hood vent | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Replace switch plate covers. | 4 | Yes | Yes. Shampoo carpet | N/A | N/A
0334 | 2 | 751 Lyndale Place North | 2 | 1084 | D | Garden | Yes | Clean carpet, replace transition strip in laundry room | Resurface | Strip and paint cabinets. | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Resurface tub in Bathroom 1. | N/A | Vanity missing one door in Bathroom 1. | N/A | Vents need replaced in bathroom 1 | Repair hole in closet door in bedroom 1, with vinyl door stop disc | N/A | N/A | N/A | N/A | N/A | Replace intake air grill. Replace switch plate covers. | 4 | Yes | Yes. Shampoo carpet | Minor trash | Remove attic access and repair
0073 | 4 | 829 Olson Memorial Hwy. Apt 302 | 2 | 953 | G3A | Garden | Yes | Clean carpet | Resurface | N/A | N/A | N/A | N/A | N/A | Remove | N/A | N/A | Resurface tub | N/A | N/A | N/A | Need toilet paper holder | N/A | N/A | N/A | Need door stops in Bedroom 2. | N/A | N/A | Replace switch plate covers. | 4 | Yes | Yes. Shampoo carpet | N/A | N/A
0073 | 4 | 851 Olson Memorial Hwy Apt. 302 | 1 | 724 | G1C | Garden | Yes | Clean Carpet | N/A | N/A | N/A | N/A | N/A | Remove | N/A | N/A | N/A | N/A | Replace vanity top | Replace vanity base | N/A | N/A | Door trim needs replaced | Hall closet doors need hardware | N/A | N/A | 1' hole in wall by front door | N/A | Replace switch plate covers. | 3 | Yes | Yes. Shampoo carpet | Major trash | Evidence of mice
0073 | 4 | 900 5th Ave. North Apt. 303 | 2 | 902 | G1D | Garden | Yes | Clean carpet, replace vinyl in kitchen | Resurface | 2 drawer fronts missing, wood cabinet. | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Resurface tub | Replace vanity top | N/A | N/A | Sprinkler head rusted | N/A | N/A | Replace lockset | Replace doors stops in bedrooms | N/A | N/A | Remove call button in Bedroom 1 | 4 | Yes | Yes. Shampoo carpet | N/A | N/A
[23 empty] | 3 | 1 | 1